| Document Title | Planning and Development |
| --- | --- |
| Document Class | Policy |
| Target Audience | All senior staff involved in planning and developing services |
| Author & Designation | Sarah Forsyth |
| Owner & Designation | Chief Nurse and Operations Officer |
| Version | 1.0 |
| CQC Domain | Well Led |
| Approved By |  |
| Approved Date |  |
| Ratified By |  |
| Ratified Date |  |
| Review Date |  |

Confidentiality Notice

This document and the information contained therein is the property of Coventry & Rugby GP Alliance (CRGPA). It must not be used by, or its contents reproduced or otherwise copied or disclosed without the prior consent in writing from CRGPA.  All or part of this document may be released under the Freedom of Information Act 2000

Table of Contents

1.	Introduction	4

2.	Purpose	4

3.	Scope	4

4.	Definitions	4

5.	Roles and Responsibilities	4

5.1    CRGPA Board	4

5.2    Chief Executive	4

5.3    Managers/Heads of Service	4

5.4    All CRGPA staff (including Bank/Contracted/Temporary Staff)	4

6.	Process	5

7.	Consultation	5

8.	Implementation	5

9.	Training and Support	5

10.	Review	5

11.	Monitoring and Compliance	6

12.	Version Control	6

13.	Equality Impact Assessment	6

14.	References	7

| # Introduction |  |
| --- | --- |
| 1.1 | Effective planning and development are essential to ensuring that Coventry and Rugby GP Alliance (CRGPA) continue to deliver high-quality, responsive, and sustainable services in a controlled manner. As the organisation evolves to meet the needs of patients, partners, and the wider health system, a consistent and transparent approach to developing new ideas, evaluating proposals, and implementing change is vital. |
| 1.2 | The CRGPA Development Group plays a central role in this process, overseeing the generation of new proposals and monitoring the progress of developments that have been formally commissioned. This policy sets out the structured Gateway Process that all service development initiatives must follow. It provides clarity on expectations, responsibilities, documentation requirements, and approval points, ensuring that every proposal is robust, evidence-based, and aligned with organisational priorities. By standardising how ideas are developed and progressed, the policy supports good governance, enhances accountability, and promotes high-quality decision-making across CRGPA. |

| # Purpose |  |
| --- | --- |
| 2.1 | The purpose of this policy is to provide a clear, consistent, and systematic approach for developing, assessing, and approving new service proposals within CRGPA. It ensures that all ideas progress through a structured Gateway Process, enabling robust planning, transparent decision-making, and effective oversight at each stage. |

| # Scope |  |
| --- | --- |
| 3.1 | This policy applies to those members of staff that are directly employed by Coventry & Rugby GP Alliance and for whom Coventry & Rugby GP Alliance has legal responsibility. For those staff covered by a letter of authority / honorary contract or work experience this policy is also applicable whilst undertaking duties on behalf of Coventry & Rugby GP Alliance or working on Coventry & Rugby GP Alliance premises and forms part of their arrangements with Coventry & Rugby GP Alliance. |

| # Definitions |  |
| --- | --- |
| 4.1 | Interdependencies Relationships or connections between projects, services, teams, or external partners where progress or outcomes in one area may impact another. |
| 4.2 | Gateway Process A structured, staged approval process used by CRGPA to assess, develop, and implement new service proposals. Each Gateway represents a decision point requiring defined documentation and approval before progressing. |

| # Roles and Responsibilities |  |
| --- | --- |
| ## 5.1 CRGPA Board |  |
|  | CRGPA Board has overall accountability for the quality and standards of care delivered by CRGPA including compliance with this policy. |
| ## 5.2 Chief Executive |  |
|  | The Chief Executive is responsible for providing overall leadership and strategic direction for the planning and development of CRGPA services. Their responsibilities include: - Ensuring organisational alignment Making sure all new proposals and developments support CRGPA’s strategic objectives, commissioning requirements, and system-wide priorities. - Accountability for governance and quality Overseeing the effectiveness of the Gateway Process and ensuring that proposals meet required standards of safety, quality, and financial viability. - Authorising progression through key stages Providing final approval for proposals that have passed through the CRGPA Development Group and require executive sign-off. - Supporting collaboration Leading engagement with external partners (e.g., PCNs, ICB, UHCW, CWPT) where proposals require joint working or shared delivery models. - Ensuring compliance Making sure all planning and development activity complies with legal, regulatory, and contractual obligations. - Promoting a culture of innovation Encouraging staff to contribute ideas and supporting the development of proposals that improve patient care and organisational performance. |
| ## 5.3 Managers/Heads of Service |  |
|  | Managers and Heads of Service play a critical role in ensuring that service development is well-planned, evidence-based, and operationally deliverable. Their responsibilities include: - Identifying opportunities for improvement Highlighting service gaps, operational challenges, or innovation opportunities that may lead to new proposals. - Developing proposals Leading or supporting the creation of Plan on a Page documents, Outline Proposals, and Detailed Proposals, ensuring they are complete, accurate, and aligned with organisational priorities. - Ensuring staff engagement Involving relevant team members in the development process and ensuring staff understand proposed changes and their implications. - Resource planning Assessing workforce, training, equipment, IT, and financial requirements for proposed services and ensuring these are clearly documented. - Risk and issue management Identifying risks early, maintaining risk registers, and escalating concerns appropriately to the Development Group. - Operational readiness Ensuring that services are prepared for implementation, including recruitment, training, pathway development, and operational processes. - Monitoring delivery Overseeing implementation activities, monitoring progress against milestones, and reporting updates to the Development Group. - Ensuring compliance Making sure that proposals and implementation plans adhere to CRGPA policies, governance requirements, and regulatory standards. - Supporting evaluation Contributing to service evaluation, audits, and project closure reports to ensure learning is captured and improvements are embedded. |
| ## 5.4 CRGPA Development Group |  |
|  | The Development Group is responsible for overseeing the structured development and approval of new service proposals. Responsibilities include: - Reviewing all submissions at each Gateway stage to ensure proposals are robust, evidence-based, and aligned with organisational priorities. - Providing constructive feedback to Project Leads and Managers to strengthen proposals. - Monitoring progress of approved developments, including risks, issues, and milestones. - Ensuring appropriate documentation is completed and stored in line with organisational requirements. - Recommending proposals for escalation to the CRGPA Board or Chief Executive where required. - Ensuring collaboration with external partners is appropriately managed for proposals requiring joint working. - Maintaining oversight of the Gateway Process to ensure consistency, transparency, and good governance. |
| 5.5 All CRGPA staff (including Bank/Contracted/Temporary Staff) |  |
|  | All staff have a responsibility to support the effective planning and development of services across CRGPA. Their responsibilities include: - Contributing to service improvement by raising ideas, concerns, or suggestions that may inform new proposals. - Participating in engagement activities, workshops, or consultations related to service development. - Providing accurate information when requested to support proposal development, activity modelling, or operational planning. - Adhering to new processes and service changes once approved and implemented. - Reporting risks or issues that may impact the delivery or success of new services. - Maintaining compliance with CRGPA policies, governance requirements, and quality standards throughout service changes. |

| # Process |  |  |
| --- | --- | --- |
| 6.1 | Gateway Process | Idea Plan on a page Outline proposal Detailed proposal (for larger scale schemes) Implementation plan, risk register and issue log Go live / monitor & evaluate Project closure report |
| 6.2 | Gateway 1 - Plan on a Page Plan on a page is to be submitted to CRGPA Development Group (appendix 1). This document is to include: - Project Name - Project Lead - Senior Responsible Officer - Clinical Lead, if applicable - Date and Version Control - Background, why this service is required - Project Outline/Description - Project Scope - Key Milestones - Interdependencies - Resource Requirements - Expected Outcomes and Measurements - Financial Assumptions - Sign off / Approval requests - Stakeholder Engagement, if required - Key Risk and Mitigations |  |
| 6.3 | Gateway 2 - Outline Proposal An outline Proposal is to be produced, and approval sought from CRGPA Development Group as well as discussed at CRGPA Board Strategy, then procced to the next Gateway (gateway 3 if external collaboration is needed, if not proceed to gateway 4). Outline of Proposal – Table of Contents: 1. Description of Proposal 2. Case for Need 3. Benefits 4. Service Scope 5. Service Model (including Clinical Design Process) 6. Activity Projections 7. Funding Model 8. Income & Expenditure Analysis 9. Implementation 10. Governance & Oversight Arrangements |  |
| 6.4 | Gateway 3 - Detailed Proposal Detailed proposals are to be produced for schemes requiring external collaboration, and approval sought from CRGPA Development Group to procced to the next Gateway. For services that require external collaboration (e.g. with CWPT or UHCW to deliver parts of service or provide clinical supervision / training): - Approval of an outline proposal will be sought to further explore the proposal with partners - This will lead to the development of a detailed proposal (appendix 2) - Table of Contents for a detailed proposal will be the same as an outline proposal - but will describe a more refined scheme and a model and arrangements agreed with external partners. |  |
| 6.5 | Gateway 4 – Implementation Detailed implementation/project plan (appendix 3) risk register and issues log to be produced and monitored by Development Group. Once go live is approaching, approval to be sought from the CRGPA Development Group to proceed to next Gateway. Aim: to clearly set out key tasks and timescales, which are then monitored. Tasks to be considered include: - Project mobilisation for implementation phase (appendix 4) - Engagement & Comms Plan - Quality Standards & Protocols - Service Specification (including KPIs) - Third Party Agreements (SLAs / Contracts) - Workforce (Recruitment / Training) - Information, Data & IT Requirements (including Data Sharing Agreements) - Audits - Medical Equipment / Consumables - Business Continuity Plan - Management Information Reporting |  |
| 6.6 | Gateway 5 – Go Live / Business as Usual Go live with the project/new service, monitor through audit and evaluate the service through feedback (appendix 5). Project closure report to be completed and submitted to CRGPA Board. Move to Business as Usual. |  |
| 6.7 | All available documents to support a new service/development plan can be found on the CRGPA drive: \\cwss.nhs.uk\ndc\CRGPADepts\Cov Rug GP Alliance\Planning & Development\04 Gateway Process and Project Template Docs\Template Documents |  |

| # Consultation |  |
| --- | --- |
| 7.1 | CRGPA Staff will have the opportunity to comment on any drafts and/or amendments to this policy via Practice Index before presentation at Policy Review Group. |

| # Implementation |  |
| --- | --- |
| 8.1 | This Policy will be available to all persons working for CRGPA. An electronic copy will be available on CRGPA’s Practice Index. |
| 8.2 | This policy will be implemented through application of the policy in practice. |

| # Training and Support |  |
| --- | --- |
| 9.1 | All employees will be offered relevant training commensurate with their duties and responsibilities. Employees requiring support should speak to their line manager in the first instance. Support may also be obtained through Human Resources. |

| # Review |  |
| --- | --- |
| 10.1 | This policy will be reviewed every three years by the Policy lead and in accordance with the following on an as and when required basis: - Legislatives changes - Good practice guidelines - Case Law - Significant incidents reported - New vulnerabilities identified - Changes to organisational infrastructure - Changes in practice |

| # Monitoring and Compliance |  |
| --- | --- |
| 11.1 | Monitoring and review of legislative changes and national/local developments which may impact on the content of this policy will be the responsibility of the Policy author and/or Policy Owner. Where any changes are required the Policy Author and/or Owner will be required to amend the policy and arrange for its presentation at the next available Policy Review Group for review and ratification. Compliance with this policy will be reviewed annually, on the anniversary of the policy ratification date. |

| # Version Control |  |
| --- | --- |
|  | Version; Date; Author (name and Designation); Comments. 1.0; May 2026 June 2026 June 2026; Sarah Forsyth, Chief Nurse and Operations Officer Daljit Sandhu, Chief Executive Officer Shashi Parekh, General Practice Support Officer; Created Reviewed and updated. Reviewed and no changes. |

| # Equality Impact Assessment |  |
| --- | --- |
| 13.1 | As part of its development, this procedural document and its impact on staff, patients and the public has been reviewed in line with Coventry & Rugby GP Alliance’s Equality Duties. The purpose of the assessment is to identify and if possible remove any disproportionate adverse impact on employees, patients and the public on the grounds of the protected characteristics under the Equality Act. |

|  |  | Yes/No |  | Comments |  |
| --- | --- | --- | --- | --- | --- |
| 1. | Does the document affect one group more or less favourably than another based on:- |  |  |  |  |
|  | Race |  | No |  |  |
|  | Religion/Religious Belief |  | No |  |  |
|  | Gender |  | No |  |  |
|  | Gender Reassignment |  | No |  |  |
|  | Sexual Orientation |  | No |  |  |
|  | Age |  | No |  |  |
|  | Any Form of Disability, impairment or mental health problems |  | No |  |  |
|  | Marriage and civil partnership |  | No |  |  |
|  | Pregnancy/Maternity |  | No |  |  |
| 2. | Is there any evidence that any groups are affected differently? |  | No |  |  |
| 3. | If any potential discrimination has been identified, are there any valid, legal or justifiable reasons? |  | NA |  |  |
| 4. | Could the document have a negative impact? |  | No |  |  |
|  | If so, can the impact be avoided/reduced? |  | NA |  |  |
|  | If not, what alternative is there to achieving the document without the negative impact? |  | NA |  |  |
| 5. | Name and Designation of 3 staff members who have contributed to or considered this assessment |  |  |  | Sarah Forsyth, Chief Nurse and Operations Officer. Daljit Sandhu, Chief Executive Officer Shashi Parekh, General Practice Support Officer |
| 6. | Date of Assessment |  |  |  | 02/06/2026 |

| 13.2 | Any potential discriminatory impact which has been identified must be referred back to the author of the document for consideration of additional actions to reduce or remove the potential discriminatory impact. |
| --- | --- |

| # References |  |
| --- | --- |

Appendix 1 – Plan on a Page

| PLAN ON A PAGE – [PROJECT NAME] / [PROJECT NUMBER] |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Lead: |  | Senior Responsible Officer |  |  |
| Clinical Lead: |  | Date / Version Control |  |  |
| Background |  |  |  |  |
| Project Outline/Description |  |  |  |  |
| Project Scope |  |  |  |  |
| Key Milestones |  |  |  |  |
| Interdependencies |  |  |  |  |
| Resource Requirements |  |  |  |  |
| Expected Outcomes & Measurements (To Primary Care/Health System/Patients/CRGPA) | Outcomes |  | Measurements |  |
| Finance Assumptions (I&E / Funding) |  |  |  |  |
| Sign Off / Approvals Reqts (Internal/External) |  |  |  |  |
| Stakeholder Engagement |  |  |  |  |
| Key Risks & Mitigations |  |  |  |  |

Appendix 2 - Detailed Proposal

Appendix 3 - Project Plan

Appendix 4 - Mobilisation Considerations

Appendix 5 - Service Evaluation Report